## 3月25日工事手順書
工事手順書：3月25日作業
行 | 項番 | 予定時刻 | 工程 | 担当者 | 項目 | 実施内容 | 確認内容 | チェック | 実施時刻
1 | 1 | 13:00 | 入館/作業準備/事前作業 |  | 入館 | 1Fフロアに集合し、サーバ室へ移動 | - |  | 12:55
2 |  |  |  |  | 作業内容意識合せ | 作業内容/役割分担を確認する | - | FALSE | 13:00
3 |  |  |  |  | 作業PC接続 | 作業PCを本部校SWに接続する IP： 接続先： | - | FALSE | 13:05
4 |  |  |  |  | NW事前ログ取得 | 「NW事前事後ログ取得」シートのログを取得 | - | FALSE | 13:30
5 | 2 | 13:30 | FW設定変更 |  | FW QoS設定変更 | 「FW作業手順」シートの手順を実施 | - | FALSE | 14:00
6 |  |  |  |  | FortiCloud設定 | 本部校FWにFortiCloudの設定を行いログ送付を行う | FortiCloudでFWログが確認できること | FALSE
7 | 4 | 14:00 | 機器撤去 |  | 本部校機器撤去 | 撤去前ラック写真撮影 | - | FALSE | 13:15
8 |  |  | ※Elementalレストアと並行で実施 |  |  | ISR4431 × 2台 初期化 | - | FALSE | 13:40
9 | [5 empty] | ISR4431 × 2台 ラック撤去 | - | FALSE | 15:00
10 | [5 empty] | IP900 × 11台 ラック撤去 | - | FALSE
11 | [5 empty] | HVX300 × 6台 ラック撤去 | - | FALSE
12 | [5 empty] | ケーブル撤去 | - | FALSE
13 | [5 empty] | 撤去後ラック写真撮影 | - | FALSE | 16:45
14 | [5 empty] | ラック周辺に残置物が無いこと | - | FALSE | 16:45
15 | [5 empty] | 返送機器梱包 | - | FALSE | 16:50
16 | [5 empty] | 返送機器をお客様へ引渡し | - | FALSE | 16:50
17 | 5 | 17:00 | 事後作業/退館 |  | NW事後ログ取得 | 「NW事前事後ログ取得」シートのログを取得 | - | FALSE | 16:30
18 |  |  |  |  | 作業内容確認、意識合せ | 作業結果を確認し、残課題があれば内容の意識合せを行う | - | FALSE | 17:00
19 |  |  |  |  | 片付け | 作業部材や梱包材を片付ける | ラックのまわりに作業の残置物やゴミが無いこと | FALSE | 17:05
20 |  |  |  |  | 退館 | - | - | FALSE | 17:10

## NW事前事後ログ取得
NW事前事後ログ取得
3/25事前ログ | FALSE | FALSE | FALSE | FALSE
3/25事後ログ | FALSE | FALSE | FALSE | FALSE
対象機器 | CEN-000-FG40_001 | CEN-000-FG40_002 | CEN-000-9200_001 | CEN-000-9200_002
コマンド | get system status | get system status | show clock | show clock
| get system arp | get system arp | terminal length 0 | terminal length 0
| get router info vrrp | get router info vrrp | terminal exec prompt timestamp | terminal exec prompt timestamp
| diagnose sys link-monitor status all | diagnose sys link-monitor status all | show version | show version
| diagnose sys ntp status | diagnose sys ntp status | show license all | show license all
| get system performance status | get system performance status | show license udi | show license udi
| get system interface | get system interface | show processes cpu | show processes cpu
| get router info routing-table all | get router info routing-table all | show processes cpu history | show processes cpu history
| get router info vrrp | get router info vrrp | show processes memory | show processes memory
| diagnose debug report | diagnose debug report | show platform software status control-processor | show platform software status control-processor
| diagnose hardware deviceinfo nic wan | diagnose hardware deviceinfo nic wan | show platform | show platform
| diagnose hardware deviceinfo nic lan1 | diagnose hardware deviceinfo nic lan1 | show platform diag | show platform diag
| diagnose hardware deviceinfo nic lan2 | diagnose hardware deviceinfo nic lan2 | show inventory | show inventory
| diagnose hardware deviceinfo nic lan3 | diagnose hardware deviceinfo nic lan3 | show environment all | show environment all
| diagnose ip router command show show int | diagnose ip router command show show int | show post | show post
| show | show | dir all-filesystems | dir all-filesystems
| show full-configuration | show full-configuration | show ip interface brief | show ip interface brief
|  |  | show interfaces description | show interfaces description
|  |  | show interfaces | show interfaces
|  |  | show interfaces status | show interfaces status
|  |  | show interfaces counters | show interfaces counters
|  |  | show interfaces counters errors | show interfaces counters errors
|  |  | show etherchannel summary | show etherchannel summary
|  |  | show etherchannel port-channel | show etherchannel port-channel
|  |  | show etherchannel load-balance | show etherchannel load-balance
|  |  | show etherchannel detail | show etherchannel detail
|  |  | show interfaces rep | show interfaces rep
|  |  | show interfaces rep detail | show interfaces rep detail
|  |  | show vlan | show vlan
|  |  | show spanning-tree | show spanning-tree
|  |  | show vtp status | show vtp status
|  |  | show ip interface | show ip interface
|  |  | show ip access-lists | show ip access-lists
|  |  | show ip protocols | show ip protocols
|  |  | show ip route | show ip route
|  |  | show ntp associations | show ntp associations
|  |  | show ntp status | show ntp status
|  |  | show archive config differences | show archive config differences
|  |  | show running-config | show running-config
|  |  | show startup-config | show startup-config
|  |  | show logging | show logging

## FW作業手順
FW作業手順
ログファイル名：ホスト名_yyyymmdd.log
行 | 対象機器 | 大項目 | 小項目 | コマンド・実施内容 | 確認内容 | チェック
1 |  | QoS設定 | shaping-policy設定 (クラス毎のトラフィックを定義) | config firewall shaping-policy edit 2 set traffic-type local-out next end |  | TRUE
2 |  | 送信元アドレス変更 | 送信元アドレスの作成 | ネットワーク > インターフェース 物理インターフェースの「wan」を編集 セカンダリIPアドレスを有効にし、新規作成をクリック IP/ネットマスクに 管理アクセスは何もチェックしない。 OKをクリック |  | TRUE
3 |  |  | 表示設定 | システム > 表示機能設定 その他の機能の「ローカルアウトルーティング」を有効 適用をクリック |  | TRUE
4 |  |  | 送信元アドレスの指定 | ネットワーク > ローカルアウトルーティング 「システムFortiguard」を編集 発信インターフェースを"wan" 送信元IPを OKをクリック |  | TRUE
5 |  |  |  | ネットワーク > ローカルアウトルーティング 「システムDNS」を編集 発信インターフェースを"wan" 送信元IPを OKをクリック |  | TRUE
6 |  |  |  | ネットワーク > ローカルアウトルーティング 「FortiGate Cloudログ」設定を編集 発信インターフェースを"wan" 送信元IPを OKをクリック |  | TRUE
7 |  |  |  | config system ntp set source-ip end |  | TRUE
8 |  | QoS確認 | QoS確認 | diagnose sys session list | 以下のエントリが存在すること shaping_policy_id： かつ、 送信元アドレス： | TRUE